## Tasks
Board
TO DO
Task ID | Task Name | Status | Assignee | Category (drop down) | Status (automatic progress)
IN PROGRESS
Task ID | Task Name | Status | Assignee | Category (drop down) | Status (automatic progress)
COMPLETE
Task ID | Task Name | Status | Assignee | Category (drop down) | Status (automatic progress)
1up25eh | Planning and documentation | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up25f0 | Robustness Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up25f1 | Sequence Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up25f3 | UML Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up26p9 | Use Case Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up26c8 | Activity Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1up25cr | Initialising Angular, TailwindCSS and MaterialUI | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1up2662 | Adding npm packages to add more functionalities to the client side | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1up25ce | Adding TailwindCSS Media dark mode | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1up25c3 | CRUD API Endpoints | COMPLETE | Sachithra Caldera | Backend | 100%
1up25bu | JWT Authorization | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxf92 | Springboot initialisation | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfak | Spring data JPA | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfba | Hibernate | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfd1 | Query DSL | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfdk | JPA Query factor | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfe0 | Maven | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfe9 | Docker | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfeq | Postgres | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxfhg | API testing using Postman | COMPLETE | Abdul Hadhi, manoj | Frontend | 100%
1uvxfj1 | MVC architecture | COMPLETE | Sachithra Caldera | Backend | 100%
1uvxg10 | Angular routing | COMPLETE | Abdul Hadhi, manoj | Frontend | 100%
1uvxg2u | JWT frontend | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1uvxg4x | Node.js | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1uvxg5x | Angular pipes and interceptors | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1uvxgbr | ER Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1uvxgc0 | Class Diagram | COMPLETE | Saranga Kanthathasan, Raviraj | Planning, Testing & Documentation | 100%
1uvxgk9 | Authguard | COMPLETE | Abdul Hadhi, Manoj | Frontend | 100%
1unzxaq | Acceptance Testing | COMPLETE | Kobiga Kunananthaseelan | Planning, Testing & Documentation | 100%
1up25bh | JUnit Test Cases | COMPLETE | Sachithra Caldera | Backend | 100%
1up25fd | Creating each frontend page accordingly | COMPLETE | manoj, Abdul Hadhi | Frontend | 100%
1uvxgdd | Black box testing | COMPLETE | Kobiga Kunananthaseelan | Planning, Testing & Documentation | 100%
1uvxgdz | White box testing | COMPLETE | Kobiga Kunananthaseelan | Planning, Testing & Documentation | 100%
1uvxgff | Sample test cases | COMPLETE | Sachithra Caldera | Planning, Testing & Documentation | 100%
1uaq1vh | Individual Documentation | COMPLETE | Kobiga Kunananthaseelan | Planning, Testing & Documentation | 100%
1uaq1vf | Planning and Testing reports | COMPLETE | Kobiga Kunananthaseelan | Planning, Testing & Documentation | 100%
1uvxgga | Azure DevOps | COMPLETE | Sachithra Caldera | DevOps | 100%
1uvxggy | Docker Containerisation | COMPLETE | Sachithra Caldera | DevOps | 100%